## Gantt Chart
Project Timeline
TITLE: Personal Project - Kanban | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: Simon | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | Story Points | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[7 empty] | JANUARY | [12 empty] | FEBRUARY
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Website Design | [5 empty] | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9
1.1 | Creating canvas | Simon | 15/1 | 19/1 | 2 | 0% | bar: JANUARY M 15 to JANUARY F 19
1.2 | Create four rectangles with different labels | Simon | 22/1 | 26/1 | 2 | 0% | bar: JANUARY M 22 to JANUARY F 26
1.3 | Backlog List | Simon | 29/1 | 2/2 | 5 | 0% | bar: JANUARY M 29 to FEBRUARY F 2
2 | Interactive list of items
2.1 | Create, update and delete story items | Simon | 15/1 | 19/1 | 13 | 0% | bar: JANUARY M 15 to JANUARY F 19
2.2 | Milestone Filter | Simon | 22/1 | 26/1 | 5 | 0% | bar: JANUARY M 22 to JANUARY F 26
2.3 | Grey out done items | Simon | 29/1 | 2/2 | 5 | 0% | bar: JANUARY M 29 to FEBRUARY F 2
3 | Create Projects
3.1 | Create JSON structure | Simon | 15/1 | 19/1 | 13 | 0% | bar: JANUARY M 15 to JANUARY F 19
3.2 | Creating different projects | Simon | 22/1 | 26/1 | 8 | 0% | bar: JANUARY M 22 to JANUARY F 26
3.3 | Select different projects | Simon | 29/1 | 2/2 | 8 | 0% | bar: JANUARY M 29 to FEBRUARY F 2
3.4 | Delete projects | Simon | 29/1 | 2/2 | 8 | 0% | bar: JANUARY M 29 to FEBRUARY F 2
3 | Documentation
3.1 | Preliminary documentation | Simon | 15/1 | 9/2 | 21 | 70%
3.2 | Code Documentation | Simon | 5/2 | 9/2 | 21 | 0% | bar: FEBRUARY M 5 to FEBRUARY F 9
3.3 | Medium Article | Simon | 5/2 | 9/2 | 21 | 0% | bar: FEBRUARY M 5 to FEBRUARY F 9