## Sprint Backlog
Epic | User Story Title | Story | Acceptance Criteria | Value | Estimate (Story Points) | Current Sprint | Sprints
Website Design | Creating canvas | As myself in the future, I want to have a template canvas so that I can easily reuse it for future projects | 1) Creating a simple canvas board with four vertical rectangles, one long list and two for future rectangles | $$$ | 2 | Sprint 1 | Name | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Interactive list of items | Create, update and delete story items | As myself in the future, I would like to have the ability to create, update and delete story items that automatically updates the board | 1) Create new items 2) Update items 3) Delete items 4) Automatic update | $$ | 13 | Sprint 1 | Start date | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05
Create Projects | Create JSON structure | As my future self, I want to be able to have a comprehensive JSON structure so that the website can run dynamically according to a template | 1) JSON template for Milestone 2) JSON template for backlog items | $$$ | 13 | Sprint 1 | End date | 2024-01-19 | 2024-01-26 | 2024-02-02 | 2024-02-09
Documentation | Preliminary documentation | As my future self, I want to have the documentation so that I can showcase my PM skills when directing a project | 1) Have SOW 2) Have Story Estimation 3) Have Project Plan 4) Have Project Schedule 5) Have Project Charter | $$$ | 21 | Sprint 1 | Point Capacity | 50 | 50 | 50 | 50
Website Design | Create four rectangles with different labels | As myself in the future, I want to have the four rectangles "To Do", "Progress", "Blocked" and "Done" so that I can track my items accordingly | 1) Have four rectangles with different labels: To Do, Progress, Blocked, Done 2) Have each rectangle with While, Yellow, Red, Green respectively | $$$ | 2 | Sprint 2 | Points Assigned | 49 | 15 | 26 | 42
Interactive list of items | Milestone Filter | As myself in the future, I want a milestone filter so that I can know which tasks I have left to do per milestone | 1) Have a filter per milestone | $$ | 5 | Sprint 2 | Value Attributed | 11 | 6 | 5 | 6
Create Projects | Creating different projects | As my future self, I want to be able to create new projects so that I can create new proejcts | 1) Be able to create new projects | $ | 8 | Sprint 2
Website Design | Backlog List | As myself in the future, I would like to have a list of all the items in the backlog so that I can see how many tasks I have left | 1) Have a list of the items broken down by epic/milestone 2) Have each epic/milestone be retractable | $$ | 5 | Sprint 3
Interactive list of items | Grey out done items | As myself in the future, I want to be able to see which items in the backlog have been marked as Done so that I can know which ones have been completed | 1) See the backlog items that are done greyed out | $ | 5 | Sprint 3
Create Projects | Select different projects | As my future self, I want to be able to select different projects so that I Can work on different projects | 2) Be able to select different projects | $ | 8 | Sprint 3
Create Projects | Delete projects | As my future self, I want to be able to delete different proejcts so that I can delete new projects | 1) Be able to delete projects | $ | 8 | Sprint 3
Documentation | Code Documentation | As my future self, I want to have the code documentation so that I know how to use my own item in the future easily | 1) Write documentation on Code 2) Have Retrospective | $$$ | 21 | Sprint 4
Documentation | Medium Article | As my future self, I want to have a medium article that would refer back to what I have created | 1) Write Medium article | $$$ | 21 | Sprint 4

## Product Backlog
Epic | User Story Title | Story | Acceptance Criteria | Value | Estimate (Story Points) | Sprint
Website Design | Creating canvas | As myself in the future, I want to have a template canvas so that I can easily reuse it for future projects | 1) Creating a simple canvas board with four vertical rectangles, one long list and two for future rectangles | $$$ | 2 | Sprint 1
Website Design | Create four rectangles with different labels | As myself in the future, I want to have the four rectangles "To Do", "Progress", "Blocked" and "Done" so that I can track my items accordingly | 1) Have four rectangles with different labels: To Do, Progress, Blocked, Done 2) Have each rectangle with While, Yellow, Red, Green respectively | $$$ | 2 | Sprint 2
Website Design | Backlog List | As myself in the future, I would like to have a list of all the items in the backlog so that I can see how many tasks I have left | 1) Have a list of the items broken down by epic/milestone 2) Have each epic/milestone be retractable | $$ | 5 | Sprint 3
Interactive list of items | Create, update and delete story items | As myself in the future, I would like to have the ability to create, update and delete story items that automatically updates the board | 1) Create new items 2) Update items 3) Delete items 4) Automatic update | $$ | 13 | Sprint 1
Interactive list of items | Milestone Filter | As myself in the future, I want a milestone filter so that I can know which tasks I have left to do per milestone | 1) Have a filter per milestone | $$ | 5 | Sprint 2
Interactive list of items | Grey out done items | As myself in the future, I want to be able to see which items in the backlog have been marked as Done so that I can know which ones have been completed | 1) See the backlog items that are done greyed out | $ | 5 | Sprint 3
Create Projects | Create JSON structure | As my future self, I want to be able to have a comprehensive JSON structure so that the website can run dynamically according to a template | 1) JSON template for Milestone 2) JSON template for backlog items | $$$ | 13 | Sprint 1
Create Projects | Creating different projects | As my future self, I want to be able to create new projects so that I can create new proejcts | 1) Be able to create new projects | $ | 8 | Sprint 2
Create Projects | Select different projects | As my future self, I want to be able to select different projects so that I Can work on different projects | 2) Be able to select different projects | $ | 8 | Sprint 3
Create Projects | Delete projects | As my future self, I want to be able to delete different proejcts so that I can delete new projects | 1) Be able to delete projects | $ | 8 | Sprint 3
Documentation | Preliminary documentation | As my future self, I want to have the documentation so that I can showcase my PM skills when directing a project | 1) Have SOW 2) Have Story Estimation 3) Have Project Plan 4) Have Project Schedule 5) Have Project Charter | $$$ | 21 | Sprint 1
Documentation | Code Documentation | As my future self, I want to have the code documentation so that I know how to use my own item in the future easily | 1) Write documentation on Code 2) Have Retrospective | $$$ | 21 | Sprint 4
Documentation | Medium Article | As my future self, I want to have a medium article that would refer back to what I have created | 1) Write Medium article | $$$ | 21 | Sprint 4