## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Creation of a simple website design | 1.1 | Create a template canvas | Front-End | 1
| 1.2 | Label four rectangles with different labels | Front-End | 1
| 1.3 | Have a list with the backlog items | Front-End | 1
Interactive list of items | 2.1 | Create, update and delete items with automatic updating | Front-End | 2
| 2.2 | Have filter according to milestone | Front-End | 1
| 2.3 | Grey out any items that are listed as done | Front-End | 1
Create, Save and Delete Projects | 3.1 | Create JSON structure | Back-End | 2
| 3.2 | Have a functionality that allows for new projects to be created | Back-End | 1
| 3.3 | Have a functionality to select different projects | Back-End | 1
| 3.4 | Have functionality to delete projects | Back-End | 1
Documentation | 4.1 | Have all of the preliminary documentation: SOW, Charter, WBS, Retrospective | Documentation | 2
| 4.2 | Ensure documentation of the code is well-created | Documentation | 2
| 4.3 | Write a Medium article about the project | Documentation | 3